## Sheet1
SPRINT #1 BACKLOG
PBI ID | PBI NAME | EFFORT POINTS | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED
9 | As a customer, I want to log in so that I can access the system's functionalities. | 8 | 9.1 | Set up database on MySql. |  |  |  | X
|  |  | 9.2 | Set up Spring project using Spring initialiser. |  |  |  | X
|  |  | 9.3 | Set up customer model, repository and API login end point. |  |  |  | X
|  |  | 9.4 | Set up Spring security. |  |  |  | X
|  |  | 9.5 | Set up react app. |  |  | X
|  |  | 9.6 | Put in navbar on home page (home page not in the sprint so can be empty page) |  |  | X
|  |  | 9.7 | Do the log-in page. |  |  | X
|  |  | 9.8 | Set up JUnit project with Mockito |  |  |  | X
|  |  | 9.9 | Perform unit test on login API end point. |  |  |  | X
|  |  | 2020-10-09 | Write acceptance testing for login functionality. |  |  |  | X
|  |  | 2020-11-09 | Investigate Mocha for front-end testing. |  | X
|  |  | 9.12 | Perform acceptance test for login functionality |  | X
43 | As a customer, I want to be able to log out so that no-one can access my data. | 1 | 43.1 | Add logout button to dynamic navbar. |  |  | X
|  |  | 43.2 | Write acceptance test for logout functionality. |  |  |  | X
|  |  | 43.3 | Perform acceptance test for logout functionality. |  | X
38 | As a Developer I want to have an accounts end point for my RESTful API so that I can perform CRUD operations on customers. | 1 | 38.1 | Create the account end point |  |  |  | X
20 | As a customer I want to be able to see my name, username, address, and contact number so that I can verify that they are correct. | 2 | 20.1 | Customer profile mockup |  |  |  | X
|  |  | 20.2 | GET customer by their Id API end point. |  |  |  | X
|  |  | 20.3 | Do a one-page customer profile page. |  |  | X
|  |  | 20.4 | Unit test for customer GET controller method. |  |  | X | X
|  |  | 20.5 | Write acceptance testing for customer profile. |  |  | X
|  |  | 20.6 | Perform acceptance testing for customer profile. |  | X