## Sheet1
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | SPRINT INTRODUCED | SPRINT COMPLETED
1 | As a developer, I want to run unit tests on GitHub action on every commit so that I can make sure my changes are not breaking anything | Taouit | High | 3 | Incomplete | All unit tests are run on every commit, unit tests are passed, changes are deployed and no functionality is broken from previous commits..
2 | As a developer, I want to continuously deploy frontend to AWS S3 to speed up deployment | Taouit | High | 3 | Incomplete | Front-end is at an accepted state for every deployment, and the client is satisfied. Front end testing has been done and completed.
3 | As a developer, I want to deploy AWS EC2 and install HSQL database to the EC2 server so that I can use it to store data | Taouit | High | 3 | Incomplete | Database and servers are all set up and able to be used for the backend. Data can be stored appropriately.
4 | As a developer, I want to kickstart the frontend project by using a react boilerplate code so that I dont have to spend time on configuration | Taouit | Medium | 3 | Incomplete | Folders are present, node modules installed, can run using npm start.
5 | As a developer, I want to continuously deploy backend to AWS EC2 server to speed up deployment | Taouit | High | 3 | Incomplete | Backend and DB is automatically deployed.
6 | As a visitor, I want to see an "about" section on the home page so that I can see if I'm interested in what the website is offering | Paula | Medium | 2 | Incomplete | Pushed into github master and release, can navigate to web-page using a link, front-end unit tested, client is satified, has sufficient information about what the web app is for.
7 | As a visitor, I want to see a "contact-us" section so that I know who to contact if I have a problem with the website. | Paula | Very High | 2 | Incomplete | Pushed into github master and release, can navigate to web-page using a link, can scroll down to see the contact us in the footer, front-end unit testing and acceptance testing passed, client is satified, has sufficient information about the contact details of the company
8 | As a visitor, I want to be able to register as a customer so that I'll be able to use the website's booking functionality. | Paula | Very High | 5 | Incomplete | Meet all the functional requirements for that functionality, Pass all tests(unit testing, integration testing, acceptance testing), pushed into master and release, client is satisfied, can see the user in the database and perform all user-related functionality on that account
9 | As a customer, I want to log in so that I can access the system's functionalities. | Paula | Very High | 8 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, user has access to all user-related functionality on web app.
10 | As an admin user, I want to be able to add a new employee to the website so that they can get some potential customers. | Paula | High | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee is there in database, employee can log-in successfully | 0
11 | As an admin user, I want to be able to edit an employee's details so that I can fix or update any errors/changes. | Paula | Medium | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee's details are updated in database appropriately
12 | As an admin user, I want to be able to edit working times for the next month so that I can fix any potential errors. | Paula | Medium | 8 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee's working times are added in database appropriately
13 | As an admin user, I want to be able to add working times for the next month so that customers can see the availabilities of employees. | Paula | Very High | 8 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, availabilities of employees are visible to customers.
14 | As a customer, I want to be able to see all the available days and times that a service is available so that I can pick a time for an appointment that best suits me. | Josiah | Very High | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied,
15 | As a customer, I want to be able to see the workers available when booking an appointment so that I can choose the worker who I want. | Aqram | High | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied,
16 | As an admin, I want to be able to look at the summary of new bookings so that I can analyse the prospectives of employees. | Aqram | Medium | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, summary of new bookings
17 | As an admin, I want to be able to look at the summary of past bookings so that I can analyse the history of employees. | Aqram | Medium | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, summary of old bookings
18 | As a customer I want to be able to see my past bookings so I know exactly how many times and when I've booked in the past. | Ian | Medium | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, see past bookings history
19 | As a customer I want to be able to edit my name, username, address, and contact number in the system so that I can change them if they are wrong or if any information changes. | Josiah | Medium | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, am able to see changes made
20 | As a customer I want to be able to see my name, username, address, and contact number so that I can verify that they are correct. | Josiah | High | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, details are laid out in an intuitive manner for the users to understand.
21 | As a customer I want to be able to cancel a booking incase I change my mind or something comes up. | Ian | Very High | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, bookings is in cancelled status on db and can see it is cancelled on dashboard | 0
22 | As a customer, I want to be able to book an appointment for a specific service with a date and a worker so that I can have that particular service done. | Josiah | Very High | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, bookings are properly put into the system.
23 | As an admin, I want to be able to sort the summary of past bookings by date so that I can find what data I want easier. | Aqram | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, sort pass bookings by date
24 | As an admin, I want to be able to sort the summary of new bookings by date so that I can find what data I want easier. | Aqram | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, sort new bookings by date
25 | As an admin, I want to view all workers’ availability for the next 7 days so that I can see when everyone is working. | Aqram | Medium | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, view employees available in 7 days
26 | As a customer I want to be able to sort my past bookings by date so that I can conveniently look for bookings within certain dates. | Ian | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), bookings are in sorted order
27 | As a user I want to see a "how it works" section on the home page so that I can see how services are offered on this website. | Taouit | High | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, can scroll and see this section on website.
28 | As an Employee I want to be able to see my profile so that I can see what services I provide and verify that my details are correct. | Taouit | High | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, can view profile with data desired by product owner
29 | As an Employee I want to be able to see my dashboard so that I can see my assigned working hours during the week. | Josiah | High | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, can view times assigned by admin
30 | As an Employee I want to be able to edit my profile so that I can update any personal details that have changed or are wrong. | Josiah | Medium | 5 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, edited details are present and change is applied to db
31 | As an Employee I want to be able to add availabilities for the next month so that I can make sure customers can see my availability and make appropriate bookings. | Taouit | High | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee's details are updated in database appropriately
32 | As an Employee I want to be able to view working times for the next month so that I can see when I am working and plan out my month. | Taouit | Medium | 3 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee can see admin's assigned working times
33 | As an Admin I want to be able to view my employees so that I can see who is working for me. | Aqram | Medium | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, admin can view employees currently working
34 | As a Customer I want to be able to view my future/pending bookings so that I can see what I have or am trying to book. | Ian | High | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, customer can view their pending bookings
35 | As a Customer I want to be able to sort my future/pending bookings so that I can easily sort them for convenience. | Ian | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, customer can sort their pending bookings
36 | As an Employee I want to be able to view my future/pending bookings so that I can see what my customers have booked. | Aqram | High | 2 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee can view future/pending bookings to view customer bookings
37 | As an Employee I want to be able to sort my future/pending bookings so that I can easily sort them for convenience. | Aqram | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee can sort future/pending bookings for convenience
38 | As a Developer I want to have an accounts end point for my RESTful API so that I can perform CRUD operations on customers. | Ian | Very High | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), | 0 | 0
39 | As a Developer I want to have an admin end point for my RESTful API so that I can perform CRUD operations on admins. | Ian | Very High | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing),
40 | As a Developer I want to have an Employee end point for my RESTful API so that I can perform CRUD operations on employees. | Ian | Very High | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing),
41 | As an Employee, I want to log in so that I can access the system's functionalities. | Taouit | Very High | 8 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, employee has access to all employee-related functionality on web app.
42 | As a Admin, I want to log in so that I can access the system's functionalities. | Taouit | Very High | 8 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, admin has access to all admin-related functionality on web app.
43 | As a customer, I want to be able to log out so that no-one can access my data. | Paula | Medium | 1 | Incomplete | Pushed into master and release branches, All the functional requirements for that functionality are implemented, Pass all tests(unit testing, integration testing, acceptance testing), client is satisfied, user can't access account functionality while logged out. | 0
General definition of done: Meet all the functional requirements for that functionality. Pass all tests(unit testing, integration testing, acceptance testing). Deployed into production. Client is satisfied.